## Standup Meeting Scrum Board
Sprint 2
2021-03-17 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Worked on owner html | finish htmls
| Lexy S. | not much | html pages, sprint docs
| Palani J. | not much | views
| Autumn A. | put issues for sprint on gitHub, reserveSpot.html | integrate more html to django
2021-03-18 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | - | -
| Lexy S. | mostly done with about.html, worked on employeeManagement.html | Finish html pages, add picture of cat
| Palani J. | Modified models and added backend api call for the map | Get js working for maps, finish api call, add verifications to models
| Autumn A. | Added html pages to Django | Finish adding html pages, start connecting to models
2021-03-19 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | finished lotManagement.html | Look at Django, suggest how to split up Django tasks
| Lexy S. | worked on html pages | finish employeeManagement.html
| Palani J. | not much | work on maps Javascript
| Autumn A. | worked on Django html pages | start adding functionality to Django
2021-03-22 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | added issues to update Django functionality | finish rendering signUp.html
| Lexy S. | not much | finish employeeManagement.html
| Palani J. | - | -
| Autumn A. | added lotManagement.html & lotInfo.html to Django | work on login.html functionality and start signUp
2021-03-23 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Added functionality to the sign up page | Finish sign up page
| Lexy S. | not much | Add picture to about page
| Palani J. | not much | Add map.html and js to django
| Autumn A. | Added login and sign up functionality | Split up tasks for reserveSpot.html
2021-03-24 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | added events and lots to signup.html and reserveSpot.html | work with Autumn on reserveSpot.html
| Lexy S. | logic behind lot attendants | edit lotManagement to add attendants, change admin management
| Palani J. | worked on maps javascript and added pictures of cats | work on maps
| Autumn A. | worked on reserveSpot.html | work with Joel on reserveSpot.html, add burndown for sprint 2
2021-03-25 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | added some more functionality | main.html functionality
| Lexy S. | burndown chart for sprint 1 and worked on about.html | work on lotManagement.html
| Palani J. | - | -
| Autumn A. | burndown chart for sprint 1 and worked on reserveSpot.html | account.html functionality
2021-03-26 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | got the conditional rendering for main.html working | finish main.html functionality
| Lexy S. | not much | work on lotManagement.html
| Palani J. | added maps to html pages | work on map.html
| Autumn A. | functionality to account.html: add balance, show reservations | get change password working on account.html
2021-03-29 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | added map to signUp.html | keep working on main.html
| Lexy S. | not much | work on lotManagement.html
| Palani J. | - | -
| Autumn A. | not much | finish account.html and sprint retrospective
2021-03-30 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Current and past reservations | complete filling out small tasks
| Lexy S. | not much | lotManagement/about tasks
| Palani J. | - | -
| Autumn A. | change password functionality and past reservations on account page | complete filling out small tasks for events and owners
2021-03-31 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | home page functionality | complete remaining tasks for home page
| Lexy S. | not much | lotManagement/about tasks
| Palani J. | map page polishing
| Autumn A. | accounts page/figured out missing functionality | get reserve spot to display only current events

## Sprint 2 Burndown
Burndown Chart: Sprint 2 (March 16-29)
Date | Tasks left | Task | Name | Date completed
|  | pastReservations.html | Joel | 2021-03-16
2021-03-16 | 23 | attendant.html | Joel | 2021-03-16
2021-03-17 | 21 | about.html | Lexy | 2021-03-24
2021-03-18 | 14 | eventManagement.html | Joel | 2021-03-16
2021-03-19 | 13 | lotInfo.html | Joel | 2021-03-17
2021-03-20 | 13 | ownerManagement.html | Joel | 2021-03-16
2021-03-21 | 13 | lotManagement.html | Joel | 2021-03-19
2021-03-22 | 10 | employeeManagement.html | Lexy | -
2021-03-23 | 8 | Django: reserveSpot.html | Autumn | 2021-03-17
2021-03-24 | 6 | Django: login.html | Autumn | 2021-03-18
2021-03-25 | 6 | Django: account.html | Autumn | 2021-03-18
2021-03-26 | 6 | Django: main.html | Autumn | 2021-03-18
2021-03-27 | 5 | Django: pastReservations.html | Autumn | 2021-03-18
2021-03-28 | 5 | Django: attendant.html | Autumn | 2021-03-18
2021-03-29 | 0 | Django: eventManagement.html | Autumn | 2021-03-18
|  | Django: ownerManagement.html | Autumn | 2021-03-18
|  | Django: lotInfo.html | Autumn | 2021-03-22
|  | Django: lotManagement.html | Autumn | 2021-03-22
|  | Django: map.html |  | 2021-03-29
|  | Django: employeeManagement.html |  | -
|  | Updated main.css file to Django | Joel | 2021-03-22
|  | Complete functionality: Login.html | Joel | 2021-03-23
|  | Complete functionality: signUp.html | Joel | 2021-03-23
|  | complete functionality: reserveSpot.html | Autumn | 2021-03-24
|  | Complete functionality: main.html | Joel | 2021-03-29
|  | Get maps working on necessary pages | Palani | 2021-03-27
|  | Finish maps API | Palani | 2021-03-29
|  | Maps Javascript | Palani | 2021-03-29
|  | Update models | Palani | 2021-03-29