## Sprint 3 Burndown
Burndown Chart: Sprint 3 (March 30- April 14)
| Task | Name | Date completed
| Complete functionality: reserveSpot (localhost:8000/reserve) | Autumn | 2021-04-14 | 2021-03-30 | 14
| Update address functionality so users don't have to enter latitude and longitude | Palani | 2021-04-14 | 2021-03-31 | 13
| Django: employeeManagement.html | Autumn | 2021-04-12 | 2021-04-01 | 13
| HTML: employeeManagement.html | Joel | 2021-04-12 | 2021-04-02 | 13
| Change the event attribute of ParkingLot to a ManytoMany attribute | Joel | 2021-04-12 | 2021-04-03 | 13
| Add totalSpots and currentSpots to ParkingSpot model | Joel | 2021-04-12 | 2021-04-04 | 12
| Complete functionality: history | Joel | 2021-04-12 | 2021-04-05 | 12
| Complete functionality: lotInfo page | Joel | 2021-04-12 | 2021-04-06 | 11
| Complete functionality: about | Lexy | 2021-04-10 | 2021-04-07 | 11
| Complete functionality: events | Autumn | 2021-04-08 | 2021-04-08 | 9
| Django: about.html | Lexy | 2021-04-08 | 2021-04-09 | 9
| Add finishing touches to spot type in registering lot owner on main | Joel | 2021-04-06 | 2021-04-10 | 9
| Complete functionality: main (localhost:8000/home) | Joel | 2021-04-04 | 2021-04-11 | 8
| HTML: Add reservation code html page OR add JS alert onClick to show code | Joel | 2021-03-31 | 2021-04-12 | 2
|  |  |  | 2021-04-13 | 2
|  |  |  | 2021-04-14 | 0

## Standup Meetings Scrum Board
Sprint 3
2021-04-05 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Main page ~almost~ done | Complete main page functionality
| Lexy S. | n/a | n/a
| Palani J. | not much | parking lot map page
| Autumn A. | Lot page functionality | reserve spot page
2021-04-08 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | lot page progres | extend conditional rendering for lot page
| Lexy S. | about page integration | about page/edit lot page
| Palani J. | database setup | parking lot map page
| Autumn A. | Lot page functionality | complete events page
2021-04-10 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | LotInfo Page
| Lexy S. | completed about page | edit lot page
| Palani J. | Lot page functionality
| Autumn A. | Many-to-many lot to event | fix some reserve spot logic
2021-04-14 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Nothing
| Lexy S. | lot edit page | complete lot edit page
| Palani J. | lat/lng api calls | attendant page
| Autumn A. | reserve spot page, takes into account all different cases | fix some reserve spot logic