## Progress Tracker
SCRUM MEETING BOARD - Group10 The Djinns
| Big Blue's Parking Genie | SPRINT LEADER | START DATE | END DATE |  | OVERALL PROGRESS
|  | Joel C. | 2021-02-23 | 2021-03-01 |  | Link
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Milestone2: Sprint 1 | [6 empty] | In Progress
| Low Fidelity Prototype 1 | Sign Up Page Wireframe | Joel C. |  | 2021-02-23 | 2021-02-24 | 1 | Complete | https://github.com/palani-johnson/TheDjinns-Group10/blob/main/docs/Prototypes/lowFidelity1_SignUpWireFrame.png
| Low Fidelity Prototype 2 | Customer Navigation Wireframe | Joel C. |  | 2021-02-24 | 2021-02-25 | 1 | Complete | https://github.com/palani-johnson/TheDjinns-Group10/blob/main/docs/Prototypes/lowFidelity2_CustomerNavigationWireframe.png
| Low Fidelity Prototype 3 | Customer Account Wireframe | Joel C. |  | 2021-02-24 | 2021-02-25 | 1 | Complete | https://github.com/palani-johnson/TheDjinns-Group10/blob/main/docs/Prototypes/lowFidelity3_CustomerAccountWireframe.png
| High Fidelity Prototype | Google Maps API | Palani J. |  | 2021-02-26 | 2021-03-01 | 3 | Complete | https://github.com/palani-johnson/TheDjinns-Group10/tree/main/docs/Prototypes/Google%20Maps
| Sprint Backlog Work |  | Lexy S. |  | 2021-02-25 | 2021-02-27 | 2 | Complete | https://github.com/palani-johnson/TheDjinns-Group10/projects/1
| Activity Diagrams |  | Autumn A. |  | 2021-02-24 | 2021-02-27 | 3 | Complete | https://github.com/palani-johnson/TheDjinns-Group10/blob/main/docs/parkingReservation.vpp
| Class Diagrams |  | Autumn A. |  | 2021-02-26 | 2021-03-01 | 3 | Complete | https://github.com/palani-johnson/TheDjinns-Group10/blob/main/docs/parkingReservation.vpp

## Sprint 2 Burndown
Burndown Chart: Sprint 2 (March 16-29)
Date | Tasks left | Task | Name | Date completed
|  | pastReservations.html | Joel | 2021-03-16
2021-03-16 | 19 | attendant.html | Joel | 2021-03-16
2021-03-17 | 17 | about.html | Lexy | 2021-03-24
2021-03-18 | 10 | eventManagement.html | Joel | 2021-03-16
2021-03-19 | 9 | lotInfo.html | Joel | 2021-03-17
2021-03-20 | 9 | ownerManagement.html | Joel | 2021-03-16
2021-03-21 | 9 | lotManagement.html | Joel | 2021-03-19
2021-03-22 | 6 | employeeManagement.html | Lexy
2021-03-23 | 4 | Django: reserveSpot.html | Autumn | 2021-03-17
2021-03-24 | 2 | Django: login.html | Autumn | 2021-03-18
2021-03-25 | 2 | Django: account.html | Autumn | 2021-03-18
2021-03-26 | 2 | Django: main.html | Autumn | 2021-03-18
2021-03-27 | 1 | Django: pastReservations.html | Autumn | 2021-03-18
2021-03-28 | 1 | Django: attendant.html | Autumn | 2021-03-18
2021-03-29 | 0 | Django: eventManagement.html | Autumn | 2021-03-18
|  | Django: ownerManagement.html | Autumn | 2021-03-18
|  | Django: lotInfo.html | Autumn | 2021-03-22
|  | Django: lotManagement.html | Autumn | 2021-03-22
|  | Django: map.html |  | 2021-03-29
Django: employeeManagement.html
|  | Updated main.css file to Django | Joel | 2021-03-22
|  | Complete functionality: Login.html | Joel | 2021-03-23
|  | Complete functionality: signUp.html | Joel | 2021-03-23
|  | complete functionality: reserveSpot.html | Autumn | 2021-03-24
|  | Complete functionality: main.html | Joel
|  | Get maps working on necessary pages | Palani | 2021-03-27
|  | Finish maps API | Palani
|  | Maps Javascript | Palani
|  | Update models | Palani

## Sprint 1 Burndown
Burndown Chart: Sprint 1 (March 1-15)
Date | Tasks left | Task | Name | Date completed
2021-03-01 | 14 | login.html | Joel | 2021-03-10
2021-03-02 | 14 | reserveSpot.html | Joel | 2021-03-10
2021-03-03 | 12 | map.html | Joel | 2021-03-10
2021-03-04 | 11 | signUp.html | Joel | 2021-03-09
2021-03-05 | 11 | Html/Css template | Joel | 2021-03-10
2021-03-06 | 10 | account.html | Joel | 2021-03-10
2021-03-07 | 10 | get website template | Joel | 2021-03-03
2021-03-08 | 10 | outline models | Autumn | 2021-03-03
2021-03-09 | 8 | set up API | Palani | 2021-03-04
2021-03-10 | 3 | signUp.html->django | Palani | 2021-03-11
2021-03-11 | 2 | rough draft models | Autumn | 2021-03-06
2021-03-12 | 2 | Update models | Palani | 2021-03-09
2021-03-13 | 2 | nav/main.html | Joel | 2021-03-15
2021-03-14 | 2 | Scrum notes for sprint | Lexy | 2021-03-15
2021-03-15 | 0

## Standup Meetings Scrum Board
Scrum Board
MILESTONE 2 -- Sprint 1/1
2021-02-23
Planning Meeting Notes:
Mtg 1: Sprint Planning 2/23/21 5:00pm - Agenda: Update/talk about GitHub Know the Beginning from the End Sprint due date: Monday -- March 1, 2021 Mtg TODO: - Estimate how many hours we have to work on this project this sprint? ~8 hr each? - Discuss availability - Discuss using milestone project points again as metric 17.5 Canvas points per person TOTAL -16 for milestone 1 revisions divied up as described below 54 / 4 = 13.5 points per person *Each person revise their specific documents from Milestone 1 as needed Revisions to milestone 1 risk analysis use case info sheets functional requirements numbering - Discuss improvements from last sprint - Assign ProjectLeader/ScrumMaster for this sprint (Milestone 2) Filling out details for stories (big picture tasks) After-mtg Tasks: - JOEL: Organize Milestones, Sprints, Tasks/Stories for GitHub moving forward - JOEL: Add all previous stories (big picture tasks) to Done column of GitHub Mtg TODO: - List stories for the sprint - Describe each of following for each story/task 1. Size estimate (pts, S/M/L) 2. Description of scope (in/out of) 3. Acceptance criteria for completion 4. List tasks for this story to be completed - created in GitHub as notes (then convert to issues assigned to a person) - assign size estimate to each (pts, S/M/L) Immediate Tasks: - JOEL: 1. Create Spring Backlog and Organize GitHub repo with Milestones, Sprints, Tasks/Stories 2. Add all previous TODO tasks to Done column of GitHub - PALANI: 1. Add in old tasks from TODOs and read commit history to ?backdate? issues 2. - Ask about in class: Use Case diagrams on Rubric - existing or new? Difference in Product Backlog requirements in Rubric Sprint Stories(to be filled out in mtg): 1. Example Story 1. Size estimate (pts, S/M/L) 2. Description of scope (in/out of) 3. Acceptance criteria for completion 4. List tasks for this story to be completed - created in GitHub as notes (then convert to issues assigned to a person) - assign size estimate to each (pts, S/M/L) PROTOTYPES: High Google maps api page Low wireframe outlining different Django views Joel - Low fidelity Lexy - Backlog Palani - Add past backlog commits to GitHub, High fidelity Autumn - Diagrams Product Backlog in GitHub repo issues (12) Stories? 10+ items (10pts) small items (2) * ask about difference in class README revisions project plan revisiosn req def revisions SAME ASSIGNMENTS AS MILESTONE 1 use case diagrams (4) ask about in class class diagrams (6) activity diagrams (6) high fidelity prototypes (12) google maps page? low fidelity prototype (10) history on scrum board showing who is working which items and when they are completed (4)
2021-02-24 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Completed 1st low fidelity prototype: Sign Up page wireframe | Complete 2nd wireframe, fill out scrum board, log hours, etc | Questions about design of navigation page for each user | Notes:
| Lexy S. | Reviewed Sprint Backlog and milestone 2 requirements | Add all requirements for Milestone 2 to Project Board/Sprint Backlog | Knowing scope of cards to add to Backlog | Joel -- Finish 2nd low fidelity wireframe Palani -- Add Django high fidelity prototype Lexy -- Get Milestone 2 backlog entries filled in Autumn -- Get Started on Activity Diagrams Activities Attendant Checking in a Customer Owner Adds Attendant Manually via Username owner types in username Reserving a Spot * add a note this is high priority get event, get lot, get open spots **Document more high priority features or processes**
| Palani J. | Started working on high fidelity prototype | Continue work on prototype, get better understanding of Google maps API | How to implement Google maps API, using git branches
| Autumn A. | Beginning work with activity diagrams | Complete some activity diagrams | Which activities to diagram?
2021-02-25 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
in class | Joel C. | Created this excel sheet | Finish low fidelity wireframes 2/3, start thinking about design of model classes/database | Knowing what classes are necessary for the database…
| Lexy S. | Added Milestone 2 items to Sprint Backlog | Add Milestone 1 cards to Sprint Backlog, breakup current items to be 1-2 workday size | Additional Future To Do column? What items to add?
| Palani J. | n/a | n/a | absent
| Autumn A. | Working with Visal Paradigm | Complete first draft Activity diagrams | What classes to diagram? What activites? Should certain activities be separate or as one larger diagram?
2021-02-25 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | 2 wireframes | Add previous reservations list to see spots you like, move current reservations tab to navigation page
| Lexy S. | see previous scrum mtg
| Palani J. | n/a | n/a | absent
| Autumn A. | 3 activity diagrams | start on class diagrams | GOOD JOB :)
2021-02-26 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | none | none
| Lexy S. | created new column in Backlog, 1 new issue | Milestone 1 cards
| Palani J. | high fidelity prototype | high fidelity prototype
| Autumn A. | none yet, more today | upload activity diagrams, work on class
2021-02-27 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | none | Finish wireframes, update progress tracker to match issues, etc on GitHub
| Lexy S. | Added ~40 issues to GitHub Sprint backlog, including past ones from Milestone 1 | Close milestone 1 issues/milestone
| Palani J. | Google Maps API started | Work more on high fidelity prototype
| Autumn A. | Worked on class diagrams | Finish class diagrams (questions about permissions vs different inherited user types | Questions about classes (good discussion)
2021-02-28
no meeting
2/29/2021 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Finished wireframes, closing issues, progress tracker
| Lexy S. | baked a cake! :)
| Palani J. | updated functional requirements | continuing to work on 'clicking' map, will tag and submit the assignment prior to M3
| Autumn A. | Finished class diagrams, updated numbers on risk analysis
MILESTONE 3
Sprint 1
2021-03-02 | Sprint Planning Mtg Notes: | Mtg 2: Sprint Planning 3/2/21 11:30 - Agenda: Update/talk about GitHub Know the Beginning from the End Sprint due date: Monday -- March 15/16, 2021 Mtg TODO: - Estimate how many hours we have to work on this project this sprint? - Discuss availability - Discuss using milestone project points again as metric *Revisions - Discuss improvements from last sprint - Assign ProjectLeader/ScrumMaster for this sprint: LEXY Filling out details for stories (big picture tasks) After-mtg Tasks: Mtg TODO: - List stories for the sprint - Describe each of following for each story/task 1. Size estimate (pts, S/M/L) 2. Description of scope (in/out of) 3. Acceptance criteria for completion 4. List tasks for this story to be completed - created in GitHub as notes (then convert to issues assigned to a person) - assign size estimate to each (pts, S/M/L) Immediate Tasks: - Review diagrams and prototypes to develop tasks - Create a list of every page/file need to create - HTML/CSS templates (front-end) JOEL email Dan/Brad about template use for front-end? 1. Logging in -- Sign Up / Login pages 2. User Navigation Page -- implement different customernav.html ownernav.html etc - Django structure (back-end) - models.py Setup the database Assignment: Autumn First step: Discuss with palani regarding interface with js google maps API - apps.py - urls.py - views.py - Handle interfacing between Javascript and Database in Django - Research *** Assignment: Palani First step: Setup database via UML/Class diagrams, work with Autumn - Ask about in class:
2021-03-03 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Website templates | download template
| Lexy S. | Learned Django | Become django expert
Palani J.
| Autumn A. | Reviewed Django | write out models
2021-03-04 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Set up sign first, sign in page | Finish sign up page, work on pages with Lexy
| Lexy S. | not much | learn more django, work on pages with Joel
| Palani J. | django/google maps | set up API, work with Autumn on classes | django and google maps aren't playing nice, use javascript?
| Autumn A. | not much | Work with Palani on classes
2021-03-08 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Sign up page, started events page | meet with Lexy, more html pages
| Lexy S. | Knows django | meet with Joel, work on html pages
| Palani J. | Worked on models | views, meet with autumn
| Autumn A. |  | models, meet with palani
2021-03-09 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | met with Lexy, finished sign in page | login and my account pages
| Lexy S. | met with Joel | work on the assigned html pages
| Palani J. | worked on models & views | more models & views
| Autumn A. | worked on models & views | more models & views
2021-03-11 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | html pages
| Lexy S. | not much
| Palani J. | not much
| Autumn A. | not much
2021-03-15 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | main.html | finish main.html
| Lexy S. | not much | finish html pages
| Palani J. | not much
| Autumn A. | looked at it | reserveSpot.html views
Sprint 2
2021-03-17 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Worked on owner html | finish htmls
| Lexy S. | not much | html pages, sprint docs
| Palani J. | not much | views
| Autumn A. | put issues for sprint on gitHub, reserveSpot.html | integrate more html to django
2021-03-18 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | - | -
| Lexy S. | mostly done with about.html, worked on employeeManagement.html | Finish html pages, add picture of cat
| Palani J. | Modified models and added backend api call for the map | Get js working for maps, finish api call, add verifications to models
| Autumn A. | Added html pages to Django | Finish adding html pages, start connecting to models
2021-03-19 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | finished lotManagement.html | Look at Django, suggest how to split up Django tasks
| Lexy S. | worked on html pages | finish employeeManagement.html
| Palani J. | not much | work on maps Javascript
| Autumn A. | worked on Django html pages | start adding functionality to Django
2021-03-22 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | added issues to update Django functionality | finish rendering signUp.html
| Lexy S. | not much | finish employeeManagement.html
| Palani J. | - | -
| Autumn A. | added lotManagement.html & lotInfo.html to Django | work on login.html functionality and start signUp
2021-03-23 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Added functionality to the sign up page | Finish sign up page
| Lexy S. | not much | Add picture to about page
| Palani J. | not much | Add map.html and js to django
| Autumn A. | Added login and sign up functionality | Split up tasks for reserveSpot.html
2021-03-24 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | added events and lots to signup.html and reserveSpot.html | work with Autumn on reserveSpot.html
| Lexy S. | logic behind lot attendants | edit lotManagement to add attendants, change admin management
| Palani J. | worked on maps javascript and added pictures of cats | work on maps
| Autumn A. | worked on reserveSpot.html | work with Joel on reserveSpot.html, add burndown for sprint 2
2021-03-25 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | added some more functionality | main.html functionality
| Lexy S. | burndown chart for sprint 1 and worked on about.html | work on lotManagement.html
| Palani J. | - | -
| Autumn A. | burndown chart for sprint 1 and worked on reserveSpot.html | account.html functionality
2021-03-26 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | got the conditional rendering for main.html working | finish main.html functionality
| Lexy S. | not much | work on lotManagement.html
| Palani J. | added maps to html pages | work on map.html
| Autumn A. | functionality to account.html: add balance, show reservations | get change password working on account.html
2021-03-29 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | added map to signUp.html | keep working on main.html
| Lexy S. | not much | work on lotManagement.html
| Palani J. | - | -
| Autumn A. | not much | finish account.html and sprint retrospective
2021-03-30 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Current and past reservations | complete filling out small tasks
| Lexy S. | not much | lotManagement/about tasks
| Palani J. | - | -
| Autumn A. | change password functionality and past reservations on account page | complete filling out small tasks for events and owners
2021-03-31 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | home page functionality | complete remaining tasks for home page
| Lexy S. | not much | lotManagement/about tasks
| Palani J. | map page polishing
| Autumn A. | accounts page/figured out missing functionality | get reserve spot to display only current events
2021-04-05 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Main page ~almose~ done | Complete main page functionality
| Lexy S. | n/a | n/a
| Palani J. | not much | parking lot map page
| Autumn A. | Lot page functionality | reserve spot page
2021-04-08 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | lot page progres | extend conditional rendering for lot page
| Lexy S. | about page integration | about page/edit lot page
| Palani J. | database setup | parking lot map page
| Autumn A. | Lot page functionality | complete events page
2021-04-10 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | LotInfo Page
| Lexy S. | completed about page | edit lot page
| Palani J. | Lot page functionality
| Autumn A. | Many-tomany lot to event | fix some reserve spot logic
2021-04-14 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Nothing
| Lexy S. | lot edit page | complete lot edit page
| Palani J. | lat/lng api calls | attendant page
| Autumn A. | reserve spot page, takes into account all different cases | fix some reserve spot logic
2021-04-15 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | testing folder | /owner and lot-info reservation totals
| Lexy S. | Lot Management is done! | Lot Edit functions
| Palani J. | Documentation | Attendant page
| Autumn A. | Burndown docs, Revenue model, etc | Implement revenue model
2021-04-19 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
| Joel C. | owner Mangement is done, readme update | demo videos
| Lexy S. | lot edit page is done, burndown | lot edit bugs
| Palani J. | attendant page is done | checkin touchup, powerpoint
| Autumn A. | created revenue model and added to account page | revenue
2021-04-20 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
| Joel C. | demo videos | 1 more video, overview writeup
| Lexy S. | finishing burndown chart | powerpoint main req slides (or autumn)
| Palani J. | powerpoint | powerpoint map req slides
| Autumn A. | various bugfixes, read up on requirements for powerpoint | powerpoint reserve req slides
2021-04-21 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
| Joel C. | overview slides
| Lexy S. | website last touches | setup database and push it
| Palani J. | preparing resources slides | finish slides
| Autumn A. | req slides